## Gantt Plan
Phase | Description | Start Date | End Date | Depends On | Milestone
Phase 0: Inception & Architecture | Project setup & architecture design | 2025-11-05 | 2025-11-18 |  | Supabase + Repo setup
Phase 1: Member & Savings Modules | Develop member registration and savings flows | 2025-11-19 | 2025-12-17 | Phase 0 | Member registration, deposit & receipt
Phase 2: Loans & Guarantorship | Implement loan workflows and guarantor logic | 2025-12-18 | 2026-01-22 | Phase 1 | Loan application, approvals & repayments
Phase 3: Automation & Notifications | Add background jobs and notifications | 2026-01-23 | 2026-02-20 | Phase 2 | Interest accruals, SMS alerts
Phase 4: Dashboards & Go-Live | Deploy dashboards and pilot branch | 2026-02-21 | 2026-03-20 | Phase 3 | Pilot live deployment
Phase 5: Post-Launch Support | Feedback, optimization, and scale-up | 2026-03-21 | 2026-04-18 | Phase 4 | Stable operations